## Description
COMP 5700/5703/6700/6706 -- Software Process
Iteration: | 2
Objective: | To gain experience with architecture
Product: | Write software to shift the tiles of a 2048 puzzle
Deliverables: | Via Canvas: | Include this spreadsheet with completed process information with your Canvas submission.
| Via GitHub: | Push your code to GitHub Classroom
| Via Cloud: | Deploy your code to IBM Cloud
Notes on Process: | - Follow the process in the "Process" worksheet for this assignment.
- This homework assignment is be accomplished individually
- Ensure you follow the course coding and counting standards.
- Be honest in your data. Your grade depends on how you follow the process and the quality of your work, not on the speed of your work or the number of defects found.
- Below are clarifications for process worksheets that have been problematic in the past:
|  | Worksheet | Special Instructions
|  | Plan | Record lines of code for production code only. Do not include test code.
|  | Acceptance | Develop acceptance tests for the specified black box. Do not include tests for items that are not part of the specifications (meaning, items over and above the specs -- these tests will appear in your individual unit test files). Write the expected results at planning time. Modify if necessary later. Don’t write actual results in advance. Actual results should reflect the state of the software at the time of delivery.
|  | Time Log | Use the "sandbox" activity to record time spent experimenting with the assignment requirements.
|  | Change Log | The "Reference to a Previous Change" column allows you to indicate that you are fixing a fix. The value in the column should be the number on the change log of the fix you are repairing.
|  | Historical Data | Record your process and product data from all previous programming assignments. Do this as part of the planning activity.
|  | Review | During the planning activity, list a count of all defects that you've previously encountered. Construct a checklist from your defect logs. Indicate during the review activity the number of times the review checklist item found an error.
|  | Scenarios | Create an interface specification depicting the interaction between a test driver and the class specified above. Create nominal scenario(s) and anomalous scenario(s) sufficient to convey your understanding of software behavior
|  | Lessons Learned | This tab is optional. Use it to record great ideas, suggestions, etc. Whining is not productive :)
|  | Architecture | Develop CRC cards only for the production code needed to implement the specifications. Do not include CRC cards for test drivers.
|  | Estimate | Record all the items from your architecture. Do not include test code.
|  | Iterations | Record the number of iterations you plan to use, together with the planned velocity of each iteration. Record the amount of time you plan to have available each day of the project window. Please plan for more than one iteration.
Special Instructions: | - Selected cells in this spreadsheet are locked against inadvertent editing. Should you need to unlock the spreadsheet, select the protected worksheet, select Tools -> Protection -> unprotect.

## Process
Constants |  |  |  | 0
Start date: | 36526 |  | Grades: | 1
End date: | 73051 |  |  | 0.95
Phases: | Analyze | Identifying customer needs |  | 0.9
| Architect | High-level design |  | 0.85
| Plan project | Determine actions/effort for project duration |  | 0.8
| Plan iteration | Determine actions/effort this iteration |  | 0.75
| Construct | Low-level design, coding, unit testing |  | 0.7
| Refactor | Restructure internal design |  | 0.65
| Review | Examine test code for risk mitigation |  | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | did not follow
| Requirements Clarification | Clarifications to requirements |  | very painful
| Product syntax | Syntax flaws in the deliverable product |  | painful
| Product logic | Logic flaws in the deliverable product |  | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | very helpful
| Test syntax | Syntax flaws in the test code
| Test logic | Logic flaws in the test code
| Test interface | Flaws in the interface of a component of the test code
| Test checking | Flaws with boundary/type checking within a component of the test code
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 0
Y/N: | Yes |  |  | 0
| No |  |  | 0
Proxy Types: | - |  |  | Base
| Calculation |  |  | New
| Data |  |  | Reusable
I/O
Logic
Sizes: | VS | S | M | VL
upper | -1.5 | -0.5 | 0.5 | 99999
mid | -2 | -1 | 0 | 2
lower | 0 | -1.5 | -0.5 | 1.5
| 0 | 0 | 0
<-- Mandatory |  | ✔
Process Script
Minimal Guiding Indicators |  |  |  | Minimal Sufficient Activities
| Goal | Indicator |  |  | Engineering Activities
| Cost: | None |  |  | Envision
| Schedule: | On time |  |  | Analyze
| Performance: |  |  |  | Synthesize
| Product: |  |  |  | Architecture
| NFR: | None |  |  | Articulate
| FR: | Equivalence Class Partitioning |  |  | Construct
| Process: | Completed spreadsheet |  |  | Interpret
Integration Test
Operational Activities
Plan
Plan project
Monitor/Control
Post Mortem
Release
Minimal Viable Process |  |  |  | Minimal Effective Practices
|  |  |  | MSA | MEP | Spreadsheet tab on which to document MEP
|  |  |  | Analyze | • Write as many acceptance tests as you feel are necessary to understand the assignment | Acceptance
|  |  |  | Architect | • Create CRC cards for each component you plan to build/modify | Architecture
|  |  |  | Plan Project | • Transfer process information from previous assignment | Historical Data
[5 empty] | • Analyze past defects and develop code review checklist | Review
[5 empty] | • Guess projected LOC | Plan
[5 empty] | • Guess projected effort (in minutes) | Plan
|  |  |  | Construction | • Repeat
• • Select/write a test case
[5 empty] | • • Run the test a red light test | Acceptance (if test is an acceptance test)
• • While the test is not red
• • • Diagnose why the test was not red
• • • If the problem was due to incorrect test code
[5 empty] | • • • • Fix the defect and log it in the change log | Change Log
• • • • Run the test as a red light test
• • • Else
• • • • Continue to the next red light test
• • Build enough production code to make the test pass
• • Run the test as a green light test
• • While the test is not green
[5 empty] | • • • Fix the defect and log it in the change log | Change Log
• • • Run the test as a green light test
• • Clean up the code as appropriate and run as blue light
• Until test coverage is sufficient and all tests pass
• Commit all code to git
|  |  |  | Review | • Perform rubber duck review of test code | Review, Change Log
|  |  |  | Refactor | • Refactor production code to remove odious smells; run as blue light | Change Log
|  |  |  | Post Mortem | • Record acceptance test results | Acceptance
[5 empty] | • Count production LOC | Plan
[5 empty] | • Record lessons learned (optional) | Lessons
|  |  |  | Release | • Commit all code to git
• Push to GitHub.com
• Upload spreadsheet to Canvas
Minimal Guiding Indicators
Cost: |  | - |  | Monitor | • Record time spent in each activity. | Time Log
Schedule: |  | Submitted on time |  |  | • Record defects, changes to requirements. | Change Log
Performance:
Product:
| NFR: | Meets delivery requirements.
| FR: | Boundary Value Analysis
| Process: | Evident on spreadsheet
Operational Engineering
Plan Project
Post Mortem
Release
Monitor
Construct
Not all components are constructed
Analyze
Review
Refactor
Failed review
Architect

## Customer Needs
Customer Needs
Background: | We are building a software representation of the 2048 sliding tile puzzle (see https://en.wikipedia.org/wiki/2048_(video_game) for an explanation of the puzzle).
Our implementation will ultimately consist of microservices that manipulate the 2048 sliding tile puzzle. Each individual microservice performs a specific function. When a microservice is passed information about the current state of the grid, it carries out its function and outputs a new grid state. The microservices serve as middleware, meaning, it operates without a user interface, and is triggered by an HTTP request. Information is carried to the microservice via a URL query string; the microservice returns information via an HTTP response. You will get some details in this assignment, with other details being explained incrementally in subsequent assignments.
This assignment asks you to write a microservice that initializes a grid.
Functional Specifications: | 2048
|  | Abstraction: | dispatch performs a specific function based on information it receives.
| method |  | description
This functionality is provided for you ➜ |  | GET /2048 | Performs an operation on the 2048 model, where the operation and any accompanying parameters are specified by the query portion of the URL
|  |  | Invocation pattern: | http://name-of-server.com/2048?op=shift&direction=d
|  |  |  | where | signifies
|  |  |  | name-of-server.com | name of the microservice provider
|  |  |  | 2048 | name of the microservice
|  |  |  | op | operation to perform ("shift," in this particular case)
|  |  |  | tiles=16 | parameters used in performing the operation ("down," in this particular case)
|  |  | Parameters: | Parameters to the microservice are specified in the query portion of the URL and must be in URL-legal format. All parameters arrive unvalidated. The "op" parameter is mandatory.
|  |  |  | Note: | If names are duplicated in the query string, the leftmost value is associated with the name.
[5 empty] | Example: | ?op=op1&op=op2
results in
"op1" being used as the value of "op"
|  |  |  | Note: | Names in the query string may be designated as empty, in which case they have an empty string as a value. This should not be interpreted as a missing parameter.
[5 empty] | Example: | ?op=op1&parm1=&parm2=
results in
empty strings being used as the values of "parm1" and "parm2"
|  |  | Desired behavior (normal): | Performs the operation named by the 'op' parameter. Returns a string of a Python dictionary containing the results. Operations are:
|  |  |  | Operation Name | Operation Description
|  |  |  | op=create | Creates a starting grid
|  |  |  | op=shift | Shifts the grid
|  |  |  | op=status | Determines whether the grid has been solved or not
|  |  |  | op=recommend | Suggests which direction to shift the grid
|  |  |  | op=info | Identifies the developer
A description of each operation is given in the "operation" section below.
|  |  | Desired behavior (errors): | If: | the query string contains no "op" parameter
|  |  |  | Action: | Return a dictionary element having a key of "status" and a value of "error: xxx", where xxx is a diagnostic string containing no quotes or apostrophes.
|  |  |  | Exit conditions: | No further processing takes place once an error is discovered.
|  |  | State change: | No state is retained by the microservice.
|  |  | General examples: | Valid values
|  |  |  | Input: | http://name-of-server.com/2048?op=create
|  |  |  | Returns: | A string of a dictionary containing the results of the "create" operation
|  |  |  | Input: | http://name-of-server.com/2048?op=shift&direction=down
|  |  |  | Returns: | A string of a dictionary containing the results of the "shift" operation
Invalid values
|  |  |  | Input: | http://name-of-server.com/2048
|  |  |  | Returns: | {'status':'error: no op is specified'}
|  |  |  | Input: | http://name-of-server.com/2048?direction=123456
|  |  |  | Returns: | {'status':'error: no op is specified'}
|  |  |  | Input: | http://name-of-server.com/2048?op=xyz
|  |  |  | Returns: | {'status':'error: op is not a legal operation'}
|  |  |  | Input: | http://name-of-server.com/2048?op=
|  |  |  | Returns: | {'status':'error: no op is specified'}
|  |  | Implementation note: | Server interface code parses the HTTP request query string into a python dictionary and passes the dictionary to _dispatch() which, in turn, calls the component associated with the specified operation. Upon completion, a dictionary containing results is returned to _dispatch() and converted to a string the HTTP response. You should not have to modify microservice.py or dispatch.py. Modules for handling each of the operations have been stubbed and require your modification.
| operation |  | description
Iteration 1 Statement of Work➜ |  | op=create | Creates a starting grid
|  |  | Invocation pattern: | http://name-of-server.com/2048?op=create
|  |  | Relevant dictionary elements: | The operation has no relevant dictionary elements (other than op)
Extraneous dictionary elements are ignored.
|  |  | Desired behavior (normal): | Returns a dictionary consisting of the following key-value pairs (see "Support Information" for examples):
|  |  |  | key | content
|  |  |  | grid | This key-value pair models the 2048 grid. Upon creation, two tiles, each having a value of 2, are randomly placed on a grid of otherwise empty tiles. The value associated with this key-value pair is a string comprised of concatenating the integer value of each of the 16 tiles in row-major order, beginning with the upper-left corner. Blank tiles are represented by "0"; non-blank tiles are represented without leading zeros.
|  |  |  | score | This key-value pair represents the score of the grid at the current point in the puzzle. It is an integer whose initial value is zero.
|  |  |  | Integrity | This key-value pair assures the integrity of the grid. Its value is the uppercase sha256 hash hexdigest of the string formed by the value of the "grid" key concatenated with a period concatenated with the string value of the "score" key.
Iteration note: This is an initial integrity check that will be changed in a later iteration.
|  |  |  | status | This key-value pair indicates the status of the game at the time the board is created. The value associated with status at creation time is "ok"
|  |  | Desired behavior (errors): | Not applicable
|  |  | General examples: | Valid values
|  |  |  | Input: | http://name-of-server.com/2048?op=create
|  |  |  | Returns: | {'grid': '0020000020000000', 'score': '0', 'integrity': '7CD5E3DEAB08FCAE8F64433DC4A63CC922571EBF60EE1D1938ADCD415FB760E5', 'status': 'ok'}
|  |  |  | Input: | http://name-of-server.com/2048?op=create
|  |  |  | Returns: | {'grid': '2200000000000000', 'score': '0', 'integrity': '0C1E79CDC2D6D5FBA1A31203029C5D951EE92DBC87CB64BA80C41D58A2DE036E', 'status': 'ok'}
Note: The random nature of the placement of the starting numbered tiles means that the same URL will likely result in a different result.
|  |  | Implementation note: | Place your code in Tiles2048/create.py; place your tests in Tiles2048/test/createTest.py . You are welcome to add functions and files as you see fit.
Iteration 1 Statement of Work➜ |  | op=info | Identifies the developer
|  |  | Invocation pattern: | http://name-of-server.com/2048?op=info
|  |  | Relevant dictionary elements: | The operation has no relevant dictionary elements (other than op=info)
Extraneous dictionary elements are ignored.
|  |  | Desired behavior (normal): | Returns a dictionary consisting of the following key-value pairs:
|  |  |  | key | content
|  |  |  | user | The value associated with the key user is your 7-character AU user name.
|  |  | Desired behavior (errors): | Not applicable
|  |  | General examples: | Valid values
|  |  |  | Input: | http://name-of-server.com/2048?op=info
|  |  |  | Returns: | {'user': 'umphrda'}
|  |  | Implementation note: | Place your code in Tiles2048/info.py; place your tests in Tiles2048/test/infoTest.py . You are welcome to add functions and files as you see fit.
|  |  | Implementation note: | Place your code in Tiles2048/info.py; place your tests in Tiles2048/test/infoTest.py . You are welcome to add functions and files as you see fit.
Iteration 2 Statement of Work➜ |  | op=shift | Shifts the grid
|  |  | Invocation pattern: | http://name-of-server.com/2048?op=shift&grid=0020000020000000&score=0&direction=up& integrity=7CD5E3DEAB08FCAE8F64433DC4A63CC922571EBF60EE1D1938ADCD415FB760E5
|  |  | Relevant dictionary elements: | key | content
|  |  |  | grid | This key-value pair models the 2048 grid. The value associated with this key-value pair is a string comprised of concatenating the integer value of each of the 16 tiles in row-major order, beginning with the upper-left corner. Blank tiles are represented by "0"; non-blank tiles are represented without leading zeros. The "Support Info" tab illustrates the layout of the grid. Mandatory. Arrives unvalidated.
|  |  |  | score | This key-value pair represents the score of the grid at the current point in the puzzle. It is a string of an even integer .GE. 0. Mandatory. Arrives unvalidated.
|  |  |  | direction | This key-value pair represents the direction in which to shift the tiles in the grid. The value is a case-agnostic string belonging to the set {'up', 'down', 'right', 'left'}. Optional; defaults to 'down' when missing. Arrives unvalidated.
|  |  |  | integrity | This key-value pair assures the integrity of the input data. Its value is the uppercase sha256 hash hexdigest of the string formed by the value of the input grid key concatenated with a period concatenated with the string value of the input score key. Mandatory. Arrives unvalidated.
Dictionary elements not specified above are ignored.
|  |  | Desired behavior (normal): | Returns a dictionary consisting of the following key-value pairs (see "Support Information" for examples):
|  |  |  | key | content
|  |  |  | grid | This key-value pair models the 2048 grid after the entire operation has taken place. The grid is first shifted in the specified direction, then either a 2 tile or a 4 tile is added in a random empty location (where the 2 tile and 4 tile have an equal chance of being added). The grid is encoded as a string comprised of concatenating the integer value of each of the 16 tiles in row-major order, beginning with the upper-left corner. Blank tiles are represented by "0"; non-blank tiles are represented without leading zeros. See the "Support Info" tab.
|  |  |  | score | This key-value pair represents the score of the grid at the current point in the puzzle. The score is calculated by adding the values of all merged tiles to the input score.
|  |  |  | Integrity | This key-value pair assures the integrity of the grid. Its value is the uppercase sha256 hash hexdigest of the string formed by the value of the "grid" key concatenated with a period concatenated with the string value of the "score" key.
Iteration note: This is an initial integrity check that will be changed in a later iteration.
|  |  |  | status | This key-value pair indicates the status of the game as of the conclusion of the operation. The value associated with the status key can have one of the following values:
[5 empty] | Value | Meaning
[5 empty] | "ok" | The grid has no 2048 tile and has at least one empty tile.
[5 empty] | "win" | A tile having the value 2048 is on the grid
[5 empty] | "lose" | The grid has no empty tiles and all tiles have a value .LT. 2048
|  |  | Desired behavior (errors): | If: | any dictionary element violates the description above
|  |  |  | Action: | Return a dictionary consisting soley of the "status" key having a value of "error:" followed by at least one space followed by a meaningful diagnostic that does not contain any apostrophes or quotes.
|  |  |  | Exit conditions: | No further processing takes place once an error is discovered.
|  |  |  | If: | the grid contains no empty tiles
|  |  |  | Action: | Return a dictionary consisting soley of the "status" key having a value of "error:" followed by at least one space followed by a meaningful diagnostic that does not contain any apostrophes or quotes.
|  |  |  | Exit conditions: | No further processing takes place once an error is discovered.
|  |  | General examples: | Nominal | Note 1: The random nature of the placement of the starting numbered tiles means that the same URL will likely result in a different result.
Note 2: These examples are illustrative and are not intended to be a comprehensive set of acceptance tests.
|  |  |  | Input: | http://name-of-server.com/2048? op=shift&grid=0020000020000000&score=0&direction=down&integrity=
|  |  |  | Returns: | {'grid': '0000004000002020', 'score': '0', 'integrity': '0DA3DEE7C5D13224BA4937CCF213B29C57676C36CDFE1C5CFC86ED069C644A17', 'status': 'ok'}
|  |  |  | Input: | http://name-of-server.com/2048? op=shift&grid=0000004024402020&score=4&direction=up&integrity= 2A2EF0D1BEA22B9D6AB67C482BFF954F93F6A3617EF052E11DD8776BFFB7325A
|  |  |  | Returns: | {'grid': '4480002000000200', 'score': '16', 'integrity': '7026D4B80CAC4E329E5224D753C487C55B859AEB2F6231C2DCEBCFD44B2C32B1', 'status': 'ok'}
|  |  |  | Input: | http://name-of-server.com/2048? op=shift&grid=0000004024402020&score=4&direction=&integrity= 2A2EF0D1BEA22B9D6AB67C482BFF954F93F6A3617EF052E11DD8776BFFB7325A
|  |  |  | Returns: | {'grid': '4000000000804420', 'score': '16', 'integrity': '96AE2C09F18145AB3B76655B47F6F9B902A48077B2DB9D365D747A801981B949', 'status': 'ok'}
|  |  |  | Input: | http://name-of-server.com/2048? op=shift&grid=2222444488881616160&score=9600&direction=left&integrity= 66457746F0596CEE48B4FA4FA9C57A8A56A917F5B42F2600F12CD4266B9098BE
|  |  |  | Returns: | {'grid': '44008800161600321602', 'score': '9688', 'integrity': 'FD4750403CBC401D7FC64E9ADCCEF7B24981481A24CFB23F274F3DC38B524883', 'status': 'ok'}
|  |  |  | Input: | http://name-of-server.com/2048? op=shift&grid=2222444488881616160&score=9600&direction=up&integrity= 66457746F0596CEE48B4FA4FA9C57A8A56A917F5B42F2600F12CD4266B9098BE
|  |  |  | Returns: | {'grid': '2222444488881616164', 'score': '9600', 'integrity': 'D0322C9B4DCAE2E0001F7BF3F24EFFE875038EA2A81660F77D14C29D7D960685', 'status': 'lose'}
|  |  |  | Input: | http://name-of-server.com/2048? op=shift&grid=1024102400000000000000&score=129024&direction=left&integrity= 18FF0FE71EB8CCFA82556511578B321D0B69A8E2FD5202EBD3A949EB35CB3C45
|  |  |  | Returns: | {'grid': '2048000000000000002', 'score': '131072', 'integrity': '51A7C485E859A94F5FFCCB25C682A66D8671ABB9AF1682756233C17499B4DE68', 'status': 'win'}
Abnormal
|  |  |  | Input: | http://name-of-server.com/2048? op=shift&grid=&score=4&direction=down&integrity= 2A2EF0D1BEA22B9D6AB67C482BFF954F93F6A3617EF052E11DD8776BFFB7325A
|  |  |  | Returns: | { 'status': 'error: missing grid'}
|  |  |  | Input: | http://name-of-server.com/2048? op=shift&grid=000000402440202a&score=4&direction=down&integrity= 2A2EF0D1BEA22B9D6AB67C482BFF954F93F6A3617EF052E11DD8776BFFB7325A
|  |  |  | Returns: | { 'status': 'error: invalid grid'}
|  |  |  | Input: | http://name-of-server.com/2048? op=shift&grid=2248161632010245120000052&score=4&direction=down&integrity= 9CE182F636152306A87BC22CDA94C8607A925E584FCF34F5896B393ACCAFD6EF
|  |  |  | Returns: | { 'status': 'error: invalid grid'}
|  |  |  | Input: | http://name-of-server.com/2048? op=shift&grid=00000040244&score=4&direction=down&integrity= 2A2EF0D1BEA22B9D6AB67C482BFF954F93F6A3617EF052E11DD8776BFFB7325A
|  |  |  | Returns: | { 'status': 'error: invalid grid'}
|  |  |  | Input: | http://name-of-server.com/2048? op=shift&grid=0000004024402020&score=33&direction=down&integrity= 1875F39BCE84620F9B3273BE921EFF1E541FEAEE10EBBF0858DB30ADF10BE2A9
|  |  |  | Returns: | { 'status': 'error: invalid score'}
|  |  |  | Input: | http://name-of-server.com/2048? op=shift&grid=0000004024402020&score=4&direction=down&integrity= B942E8D41B41814866B32EA9C9A3A4205ABA77148D86741D1EFE765BE6FEAADB
|  |  |  | Returns: | { 'status': 'error: bad integrity value'}
|  |  |  | Input: | http://name-of-server.com/2048? op=shift&grid=0000004024402020&score=4&direction=back&integrity= 2A2EF0D1BEA22B9D6AB67C482BFF954F93F6A3617EF052E11DD8776BFFB7325A
|  |  |  | Returns: | { 'status': 'error: invalid direction'}
|  |  |  | Input: | http://name-of-server.com/2048? op=shift&grid=2222222222222222&score=4&direction=down&integrity= 96D0C2876B9E858F6BA247A8E944DA7D76F55E6026017A5C4A0B9B128C16F844
|  |  |  | Returns: | { 'status': 'error: no shift possible'}
Note: The random nature of the placement of the starting numbered tiles means that the same URL will likely result in a different result.
|  |  | Implementation note: | Place your code in Tiles2048/shift.py; place your tests in Tiles2048/test/shiftTest.py . You are welcome to add functions and files as you see fit.
Future Iteration ➜ |  | op=status | Determines whether the grid has been solved or not
|  |  | Desired behavior (normal): | Currently stubbed
Future Iteration ➜ |  | op=recommend | Suggests which direction to shift the grid
|  |  | Desired behavior (normal): | Currently stubbed

## Spec Notes (hidden)
Specification Notes

## Support Info
2048 Sliding Tile Puzzle
We are building a 2048-like game consisting of 16 tiles arranged in a 4 x 4 square. At the start of play, two "2" tiles are randomly placed on empty grid. The player indicates whether the tiles should be shifted in one of four directions: up, down, left, right. All tiles are moved as far as possible in the specified direction, filling empty grid elements, and a new tile (having a value 2 or 4) is randomly placed in an empty grid element. If two tiles having the same number collide while being shifted, they merge into a single tile whose value is the sum of the numbers on the collided tiles. The player's score is the tally of each merged tile's value. The game is won when 2048 appears on a merged tile. It is lost when no tiles can be shifted.
More info: | https://en.wikipedia.org/wiki/2048_(video_game)
https://www.mathsisfun.com/games/2048.html
Envisioning the grid
You can envision the grid as being a 4 x 4 matrix:
| Tile 1 | Tile 2 | Tile 3 | Tile 4
| Tile 5 | Tile 6 | Tile 7 | Tile 8
| Tile 9 | Tile 10 | Tile 11 | Tile 12
| Tile 13 | Tile 14 | Tile 15 | Tile 16
Translating a grid into a string
The op=create microservice randomly places two "2" tiles on an otherwise empty grid, resulting in a grid similar to what is shown below. The starting score is 0.
| Empty | Empty | 2 | Empty
| 2 | Empty | Empty | Empty
| Empty | Empty | Empty | Empty
| Empty | Empty | Empty | Empty
The microservice returns the grid as a string comprised of concatenating the integer value of each of the 16 tiles in row-major order, beginning with the upper-left corner:
0020200000000000
Given that the initial score is 0, the integrity value is the sha256 hash digest of 0020200000000000.0, which is
EC95688C10834B7C4AAE0017B8DAD3F747752CE69AA34CD92EB605AEC9D97EA1
Translating a string into a grid
While the op=create operation yields a grid in string format, other operations require a grid be passed as an input parameter. The following string
224816163201024512000000
would result in the grid below:
| 2 | 2 | 4 | 8
| 16 | 16 | 32 | Empty
| 1024 | 512 | Empty | Empty
| Empty | Empty | Empty | Empty
Shifting a grid
See "Gameplay" at https://en.wikipedia.org/wiki/2048_(video_game) for a description of how shifting takes place.

## Assessment
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1
End date: | 73051 |  |  | A | 0.95
Phases: | Analyze | Identifying customer needs |  | AB | 0.9
| Architect | High-level design |  | B | 0.85
| Plan project | Determine actions/effort for project duration |  | BC | 0.8
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75
| Construct | Low-level design, coding, unit testing |  | CD | 0.7
| Refactor | Restructure internal design |  | D | 0.65
| Review | Examine test code for risk mitigation |  | F | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful
| Test syntax | Syntax flaws in the test code |  | 6
| Test logic | Logic flaws in the test code |  | 7
| Test interface | Flaws in the interface of a component of the test code |  | 8
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0
Y/N: | Yes |  |  | Passed | 0
| No |  |  | Passed with issues | 0
Proxy Types: | - |  |  | Failed | Base
| Calculation |  |  | Not tested | New
| Data |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS | S | M | L | VL
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999
mid | -2 | -1 | 0 | 1 | 2
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5
| 0 | 0 | 0 | 0
<-- Mandatory |  | ✔
Assessment Worksheet
Name: |  | Sarah Pham
User name: |  | slp0042
GitHub user name: |  | phamsarah
URL of microservice: |  | https://slp0042-2048.mybluemix.net/
Instructor Assessment
Product Assessment
Process Assessment:
Score: |  | out of | 100
Grading rubric: Product Aspect
| AA | 100 | Exceptional job worthy of being used as an example of superior work
| A | 95 | Product satisfies all functional requirements, has insignificant nonfunctional requirement nonconformance
| AB | 90 | Product satisfies all functional requirements, has minor nonfunctional requiement nonconformance
| B | 85 | Product satisfies all functional requirements, has major nonfunctional requirement noncomformance
| BC | 80 | Product encounters minor functional deviations, has insignificant nonfunctional requirement nonconfirmance
| C | 75 | Product encounters minor functional deviations, has minor nonfunctional requirement nonconfirmance
| CD | 70 | Product encounters minor functional deviations, has major nonfunctional requirement nonconfirmance
| D | 65 | Product encounters multiple significant problems in functional and/or nonfunctional requirements
| F | 50 | Deliverables show lack of comprehension of concepts, or are incomplete
Grading rubic: Process Aspect
| AA | 100 | Exceptional job worthy of being used as an example of superior work
| A | 95 | Process has insignificant exceptions
| AB | 90 | Process has multiple minor exceptions
| B | 85 | Process has exceptions that obsure activity verification
| BC | 80 | Process has exceptions with historical data that affect the current project
| C | 75 | Process has exceptions that suggest lack of comprehension of concepts
| CD | 70 | Process has exceptions that bring into question the validity of the data
| D | 65 | Process has exceptions suggesting it wasn't followed.
| F | 50 | Deliverables are incomplete
Quality checks |  |  | changes from the previous assignment are in red
General
Are all regions highlighted in yellow appropriately complete?
Does the workbook reflect a faithful record of information?
Has this assignment been uploaded as specified by the assignment description?
Project Plan Summary
Was the planned information determined before development and not altered after development?
Is planned time expressed in minutes?
Do LOC counts address production code (and exclude test code)?
Is the actual line count calculated according to the counting standard?
Time Recording Log
Does the log reflect a faithful record of time spent?
Do no times span midnight?
Does the log reflect the activities in the specified process?
Is post mortem the final phase?
Does the time recording log reflect the your lifecycle?
Change Log
Is each change accompanied by a description in the "comment" field?
Are changes recorded against the appropriate phase in which they were injected and removed?
Does the "removed" count equal the "injected" count? If not, is the rational documented in the "lessons learned" tab?
Are the dates and times in the change log consistent with the dates and times in the time recording log?
Acceptance Report
Do actual results support expected results?
Do actual results marked as "Passed with issues" include a comment?
Source Code
Does the code reflect the coding standard?
Will the code compile without change?
Does the production code contain any packages that aren't part of the customer's production environment.
Does the code take into consideration specified error conditions?
Does the code fulfill the assignment requirements?
Does the code follow the prescribed directory format (i.e., prod, test, sandbox)?
Historical Data
Is the historical data complete?
Have previously noted problems in process measurements been corrected?
Deliverables
Has the spreadsheet been uploaded to Canvas?
Has all the code been pushed to GitHub?
Is test code in a separate folder?
Will the test code work without modification?
Does the git respository reflect commits at the specified process points?
Does the "Assessment" tab include your name, your AU username, etc.
Review
Did you construct your review checklist during the planning phase?
Does the error count indicated the analysis of defects match your historical defect count?
Are checklist items answerable in "yes" or "no" terms?
Does your checklist reflect at least one common item from your defect log ?
Does your checklist contain more than contrived "mom and apple pie" items?
Refactor
Is code free of the following bad smells: duplicate code, long methods, long classes
temporary variables, useless comments, coding standard violations?
Scenario
Were the scenarios constructed during the analysis phase (and not changed later)?
Does each scenario describe as fully as possible the interaction with the software under construction?
Are the actors correctly identified?
Are suitably understandable examples given?
Are events and responses directly observable?
Architecture
Was the architecture determined before construction (and not changed later)?
Does the architecture reflect a solid initial understanding of the solution?
Does the architecture show all components required for the solution (with the exception of system built-in components)?
Are collaborators specified correctly?
Do functionally-decomposed components have only one operation? Has the operation been given the component name?
Are component operations given names to suggest their behavior?
Does the architecture exhibit "good" design characteristics, such as appropriate levels of coupling, cohesion, etc.?
Estimate
Does each component denoted by a CRC card appear in the estimate as either base code, new components, or reused code?
Is base code vs reuse code identified correctly?
Do the base components and the new comopnents reflect the architecture?
Are the base components and new components sized according to historical proxies?
Is a rationale provided if either the LOCp and/or Ep are overridden?
Does the value of LOCa reflect effort expended on creating, adding, or modifying production code?
Is actual LOC data recorded at post mortem time?
Iterations
Is more than one iteration planned?
Does the WBS list all iterations?
Is the overall estimate of time in the WBS consistent with the calculated effort?
Are the planned completion dates of iterations in the WBS consistent with the calendar?
Are planned times recorded from the start of the calendar through the end of the project?
Does the calendar corroborate the WBS, and visa versa?
Construction
Did you follow the design -> test(failure) -> code -> test(success) -> clean up (if necessary) -> repeat pattern?
Are all unit tests written so that passing the test satisifies requirements?
Are unit tests written to the level of boundary value analysis?
Is there at least one test suite which, when run, exercises the entire production code base?
Does your code pass all test cases?

## Historical Data
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1
End date: | 73051 |  |  | A | 0.95
Phases: | Analyze | Identifying customer needs |  | AB | 0.9
| Architect | High-level design |  | B | 0.85
| Plan project | Determine actions/effort for project duration |  | BC | 0.8
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75
| Construct | Low-level design, coding, unit testing |  | CD | 0.7
| Refactor | Restructure internal design |  | D | 0.65
| Review | Examine test code for risk mitigation |  | F | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful
| Test syntax | Syntax flaws in the test code |  | 6
| Test logic | Logic flaws in the test code |  | 7
| Test interface | Flaws in the interface of a component of the test code |  | 8
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0
Y/N: | Yes |  |  | Passed | 0
| No |  |  | Passed with issues | 0
Proxy Types: | - |  |  | Failed | Base
| Calculation |  |  | Not tested | New
| Data |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS | S | M | L | VL
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999
mid | -2 | -1 | 0 | 1 | 2
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5
| 0 | 0 | 0 | 0
Historical Data
Current Assignment: |  | Assignment 6 | CAAssignment 6.xls
Immediate Past Assignment: |  | Assignment6 | 202120Assignment4
As of the end of |  |  | 202120Assignment4
|  | 202120Assignment4 | 202120Assignment4 | All previous
Program Size (LOC) |  | LOCp | LOCa | LOCa
Base code LOC count
Lines deleted from Base
Lines modified from Base
Lines added to Base
Reused lines
New lines of production code |  |  |  | 0
Component Count |  | Plan | Actual | Actual to Date
Reused components |  |  |  | 0
Modified components |  |  |  | 0
New components |  |  |  | 0
|  | 202120Assignment4 | 202120Assignment4 | All previous
Time In Phase (minutes) |  | Ep | Ea | Ea | To Date %
Analyze |  |  |  |  | 0%
Architect |  |  |  |  | 0%
Plan project |  |  |  |  | 0%
Plan iteration |  |  |  |  | 0%
Construct |  |  |  |  | 0%
Refactor |  |  |  |  | 0%
Review |  |  |  |  | 0%
Integration test |  |  |  |  | 0%
Repattern |  |  |  |  | 0%
Postmortem |  |  |  |  | 0%
Sandbox |  |  |  |  | 0%
TOTAL |  |  |  | 0 | 0%
All previous
Changes traced to the activities below: |  |  | 202120Assignment4 | changes | To Date %
Analyze |  |  |  |  | 0%
Architect |  |  |  |  | 0%
Plan project |  |  |  |  | 0%
Plan iteration |  |  |  |  | 0%
Construct |  |  |  |  | 0%
Refactor |  |  |  |  | 0%
Review |  |  |  |  | 0%
Integration test |  |  |  |  | 0%
Repattern |  |  |  |  | 0%
Postmortem |  |  |  |  | 0%
Sandbox |  |  |  |  | 0%
TOTAL |  |  |  | 0 | 0%
App previous
Changes implemented in the activities below: |  |  | 202120Assignment4 | changes | To Date %
Analyze |  |  |  |  | 0%
Architect |  |  |  |  | 0%
Plan project |  |  |  |  | 0%
Plan iteration |  |  |  |  | 0%
Construct |  |  |  |  | 0%
Refactor |  |  |  |  | 0%
Review |  |  |  |  | 0%
Integration test |  |  |  |  | 0%
Repattern |  |  |  |  | 0%
Postmortem |  |  |  |  | 0%
Sandbox |  |  |  |  | 0%
TOTAL |  |  |  | 0 | 0%
Size Matrix (LOC/Method)
| Lower | Mid | Upper
VS
S
M
L
VL
Project History
| New and Changed LOC |  |  | Effort
Project Name | Raw LOC | Planned LOC | Actual LOC | Estimated Time | Actual Time | LOCa/LOCr | Ea/LOCa
1.xls | 0 |  |  |  |  | 0 | 0
CA02 | 0 |  |  |  |  | 0 | 0
3.xls | [5 empty] | 0 | 0
CA04 | 0 |  |  |  |  | 0 | 0
CA05 |  | 0 | 0 | 0 | 0 | 0 | 0
Project Trends
Productivity= |  | LOC/hr
Average size= | 13 | LOC/method
Component History
Component Name |  | Total LOC | Method Count | Type | Size | LOC/method | ln(LOC/meth)
_dispatch |  | 13 | 1 | Logic | #REF! | 13 | 2.5649
_create |  |  |  | - | -
_info |  |  |  | - | - |  |  | `
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
[6 empty] | Average= | 2.5649
[6 empty] | Std= | 0
Note on C57: Estimate the number of new lines of code that provide new functionality to meet the specifications of this assignment.
Note on C61: Estimate of the number of previously-written components that require modification
Note on C62: Estimate of the number of entirely new components

## Review
Review
Standards
Start date: | 2000-01-01 |  | Grades: |  |  | AA
End date: | 2020-01-01 |  |  |  |  | A
Phases: | Analysis |  |  |  |  | AB
| Architecture |  |  |  |  | B
| Planning |  |  |  |  | BC
| Construction |  |  |  |  | C
| Refactoring |  |  |  |  | CD
| Review |  |  |  |  | D
| Integration Test |  |  |  |  | F
Postmortem
Sandbox
Defect Types: | Documentation |  | Iteration |  |  | NA
| Build |  |  |  |  | 1
| Product syntax |  |  |  |  | 2
| Product logic |  |  |  |  | 3
| Product interface |  |  |  |  | 4
| Product checking |  |  |  |  | 5
| Test syntax |  |  |  |  | 6
| Test logic |  |  |  |  | 7
| Test interface |  |  |  |  | 8
| Test checking |  |  |  |  | 9
| Bad Smell |  |  |  |  | 10
Y/N: | Yes
No
Proxy Types: | Calculation
Data
I/O
Logic
Sizes: | VS
S
M
L
VL
Defect Pareto Analysis (taken from all defects to date)
| Type | Description |  | Count of Occurrences | %
| Requirements Change | Changes to requirements
| Requirements Clarification | Clarifications to requirements
| Product syntax | Syntax flaws in the deliverable product
| Product logic | Logic flaws in the deliverable product
| Product interface | Flaws in the interface of a component of the deliverable product
| Product checking | Flaws with boundary/type checking within a component of the deliverable product
| Test syntax | Syntax flaws in the test code
| Test logic | Logic flaws in the test code
| Test interface | Flaws in the interface of a component of the test code
| Test checking | Flaws with boundary/type checking within a component of the test code
| Bad Smell | Refactoring changes (please note the bad smell in the defect description)
|  |  | Total | 0 | 0%
Code Review Checklist
| Item |  |  | Number of times this item detected a defect during review

## Acceptance
Constants | [5 empty] | 0
Start date: | 36526 |  |  | Grades: | AA | 1 | 0
End date: | 73051 |  |  |  | A | 0.95 | 0
Phases: | Analyze |  | Identifying customer needs |  | AB | 0.9 | 0
| Architect |  | High-level design |  | B | 0.85 | 0
| Plan project |  | Determine actions/effort for project duration |  | BC | 0.8 | 0
| Plan iteration |  | Determine actions/effort this iteration |  | C | 0.75 | 0
| Construct |  | Low-level design, coding, unit testing |  | CD | 0.7 | 44296
| Refactor |  | Restructure internal design |  | D | 0.65 | 44297
| Review |  | Examine test code for risk mitigation |  | F | 0.5 | 44298
| Integration test |  | End-to-end test of components to date |  |  |  | 44299
| Repattern |  | Restructure external design |  |  |  | 44300
| Postmortem |  | Capture post-development statistics |  |  |  | 44301
| Sandbox |  | Prove ideas, try concepts |  |  |  | 44302
44303
44304
44305
#REF!
Defect Types: | Requirements Change |  | Changes to requirements | Iteration | NA | did not follow | #REF!
| Requirements Clarification |  | Clarifications to requirements |  | 1 | very painful | #REF!
| Product syntax |  | Syntax flaws in the deliverable product |  | 2 | painful | #REF!
| Product logic |  | Logic flaws in the deliverable product |  | 3 | neutral | #REF!
| Product interface |  | Flaws in the interface of a component of the deliverable product |  | 4 | helpful | #REF!
| Product checking |  | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful | #REF!
| Test syntax |  | Syntax flaws in the test code |  | 6 |  | #REF!
| Test logic |  | Logic flaws in the test code |  | 7 |  | #REF!
| Test interface |  | Flaws in the interface of a component of the test code |  | 8 |  | #REF!
| Test checking |  | Flaws with boundary/type checking within a component of the test code |  | 9 |  | #REF!
| Bad Smell |  | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0 | #REF!
Y/N: | Yes |  |  |  | Passed | 0 | #REF!
| No |  |  |  | Passed with issues | 0 | 44319
Proxy Types: | - |  |  |  | Failed | Base | 44320
| Calculation |  |  |  | Not tested | New | 44321
| Data |  |  |  | Not applicable | Reusable | 44322
| I/O | [5 empty] | 44323
| Logic | [5 empty] | 44324
44325
Sizes: | VS |  | S | M | L | VL | VS
upper | -1.5 |  | -0.5 | 0.5 | 1.5 | 99999 | S
mid | -2 |  | -1 | 0 | 1 | 2 | M
lower | 0 |  | -1.5 | -0.5 | 0.5 | 1.5 | L
| 0 |  | 0 | 0 | 0 |  | VL
Acceptance Test Report
Use this worksheet to record tests that, if passed, tell you that your software is complete. It is not a chronology, so do not list a history of tests. List only tests that are directly linked to requirements (in other words, do not list tests for methods or components that you create over and above what is required to fulfill the specified interface definition -- these tests will appear in your individual unit test files). Write the expected results at planning time. Modify if necessary later. Don’t write actual results in advance.
Requirements:
op=create
op=shift
op=status
op=recommend
op=info
Requirement | Test Description | Test | Expected Results |  | Actual Results | Issues
op=shift | Test logic | test_shift_navigatesToShiftHappyPath -> Tests if the shift file is being called correctly | Flaws in the interface of a component of the test code |  | Passed | None
op=shift | Test logic | test_shouldReturnAddedLeftGrid -> Tests if the grid will add in the left direction | Flaws in the interface of a component of the test code |  | Passed | None
op=shift | Test logic | test_shouldReturnAddedUpGrid -> Test to see if the grid will add in Up direction | Flaws in the interface of a component of the test code |  | Passed | None
op=shift | Test logic | test_shouldReturnAddedRightGrid -> Test to see if the grid will add in Right direction | Flaws in the interface of a component of the test code |  | Passed | None
op=shift | Test logic | test_shouldReturnAddedDownGrid -> Test to see if the grid will add in Down direction | Flaws in the interface of a component of the test code |  | Passed | None
op=shift | Test Logic | test_shouldAddRandomNumber -> Test to see if a random number is generated and added to a correct spot | Flaws in the interface of a component of the test code |  | Passed | None
op=shift | Test logic | test_shouldReturnCorrectScore -> Test to see if a score is calculated correctly | Flaws in the interface of a component of the test code |  | Passed | None
op=shift | Test logic | test_shouldReturnCorrectStatus -> Test to see if a Status is calculated correctly | Flaws in the interface of a component of the test code |  | Passed | None
op=shift | Test logic | test_ExceptionHandling_MissingGrid -> Test a missing grid | Flaws with boundary/type checking within a component of the test code |  | Passed | None
op=shift | Test logic | test_ExceptionHandling_BadIntegrityValue -> Test a bad integrity value | Flaws with boundary/type checking within a component of the test code |  | Passed | None
op=shift | Test logic | test_ExceptionHandling_InvalidScore -> Test invalid score | Flaws with boundary/type checking within a component of the test code |  | Passed | None
op=shift | Test logic | test_ExceptionHandling_InvalidGrid -> Test invalid grid | Flaws with boundary/type checking within a component of the test code |  | Passed | None
op=shift | Test logic | test_ExceptionHandling_InvalidDirection -> Test invalid direction | Flaws with boundary/type checking within a component of the test code |  | Passed | None
op=shift | Test logic | test_ExceptionHandling_NoShiftPossible -> Test no shift possible | Flaws with boundary/type checking within a component of the test code |  | Passed | None
Note on A51: Establish traceability between the tests and requirements.
Note on B51: Defines observable tests that have quantifiable resutls.
Note on D51: Specifies the result that that the test is anticipated to produce.
Note on F51: Defines the result of running the test in relation to the expected result.
Note on G51: Required whenthe actual result is "Passed with issues"; optional otherwise. An "issue" is a side-effect that is not part of the specified test.

## Map (hidden)
Sceneario-Component Map
X
Component Names:
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## Architecture
Architecture
Use this worksheet to describe components required to implement the specifications. List new components and base components. Do not include extraneous components. | Use this worksheet to describe components required to implement the specifications. List new components and base components. Do not include extraneous components.
Standards
| Start date: | 2000-01-01
| End date: | 2010-01-01
| Phases: | Planning
Design
Design Review
Code
Code Review
Compile
Test
Postmortem
| Defect Types: | Documentation
Syntax
Build, Package
Assignment
Interface
Checking
Data
Function
System
Environment
| Y/N: | Yes
No
| Component Types: | Calculation
Data
I/O
Logic
| Design Approaches: | Object-oriented
Functional
| Sizes: | VS
S
M
L
VL
| Duration: | LOCe x T
LOCa x T
Productivity
1 | Component Name: | Shift
| Design Approach: | Object-oriented
Parent Component:
Attributes (optional):
| Component Type: | Logic
| Collaborators: | Sarah Pham
| Operations: | Will move the given grid string according to the given direction and error check.
2 | Component Name: | errorReturnStatus
| Design Approach: | Object-oriented
| Parent Component: | Shift
Attributes (optional):
| Component Type: | Logic
| Collaborators: | Sarah Pham
| Operations: | Returns the status if there is an error with any given parameter
3 | Component Name: | validateInputParameters
| Design Approach: | Object-oriented
| Parent Component: | Shift
Attributes (optional):
| Component Type: | I/O
| Collaborators: | Sarah Pham
| Operations: | Validates the input parameters
4 | Component Name: | validateIntegrity
| Design Approach: | Object-oriented
| Parent Component: | Shift
Attributes (optional):
| Component Type: | I/O
| Collaborators: | Sarah Pham
| Operations: | Validates the given integrity value, will check the value after the grid input is checked as valid.
5 | Component Name: | moveTile
| Design Approach: | Object-oriented
| Parent Component: | Shift
Attributes (optional):
| Component Type: | I/O
| Collaborators: | Sarah Pham
| Operations: | Calls the function that will move the tile in terms of direction and sends the direction column
6 | Component Name: | moveInDirection
| Design Approach: | Object-oriented
| Parent Component: | Shift
Attributes (optional):
| Component Type: | I/O
| Collaborators: | Sarah Pham
| Operations: | Moves the tile in terms of the given direction, will add any random 2, and calls function to check status
7 | Component Name: | checkStatus
| Design Approach: | Object-oriented
| Parent Component: | Shift
Attributes (optional):
| Component Type: | I/O
| Collaborators: | Sarah Pham
| Operations: | Will check the status of any given list
8 | Component Name: | addRandomTwo
| Design Approach: | Object-oriented
| Parent Component: | Shift
Attributes (optional):
| Component Type: | I/O
| Collaborators: | Sarah Pham
| Operations: | Will add a random 2 to the given grid list.
9 | Component Name: | createGridList
| Design Approach: | Object-oriented
| Parent Component: | Shift
Attributes (optional):
| Component Type: | I/O
| Collaborators: | Sarah Pham
| Operations: | Converts the given string into a list format since the string index does not represent the tile index
10 | Component Name: | validate2048
| Design Approach: | Object-oriented
| Parent Component: | Shift
Attributes (optional):
| Component Type: | I/O
| Collaborators: | Sarah Pham
| Operations: | Validates a '2048', in some cases there may be a 2048 that is not actually a 2048 but a separate 2-0-4-8-
| Component Name: | findNumber
| Design Approach: | Object-oriented
| Parent Component: | Shift
Attributes (optional):
| Component Type: | I/O
| Collaborators: | Sarah Pham
| Operations: | Checks if the given string is a valid '2048 game' number.
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Note on B43: Identifying name for this design class or function.
Note on B44: Indicate if this design component will follow an object-oriented approach or a functional approach.
Note on B45: Superclass of this design component. Leave blank if no superclass.
Note on B46: Attributes (e.g., public fields, public constants) associated with this design component. OPTIONAL
Note on B47: Standard category of the design component.
Note on B48: List components that this component calls upon to fulfill its purpose.
Note on B49: Description of the operations of this design component. If your are taking an object-oriented approach, list the methods associated with this object in the "operation" column. If you are taking a functional approach, list the component name in the "operation" column. Note: an object-oriented approach may result in zero or more operations; a functional approach will have only one operation listed.

## Estimation (hidden)
Size Estimate
Constants |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Start date: | 36526 |  | Grades: | AA | 1 | 0 | 44305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
End date: | 73051 |  |  | A | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phases: | Analyze | Identifying customer needs |  | AB | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Architect | High-level design |  | B | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Plan project | Determine actions/effort for project duration |  | BC | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construct | Low-level design, coding, unit testing |  | CD | 0.7 | 44296 | 0 | 0 | AM | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Refactor | Restructure internal design |  | D | 0.65 | 44297 | 1 | 5 | PM | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Review | Examine test code for risk mitigation |  | F | 0.5 | 44298 | 2 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integration test | End-to-end test of components to date |  |  |  | 44299 | 3 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Repattern | Restructure external design |  |  |  | 44300 | 4 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Postmortem | Capture post-development statistics |  |  |  | 44301 | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sandbox | Prove ideas, try concepts |  |  |  | 44302 | 6 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 44303 | 7 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 44304 | 8 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 44305 | 9 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 44306 | 10 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow | 44307 | 11 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful | 44308 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful | 44309 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral | 44310 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful | 44311 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful | 44312 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test syntax | Syntax flaws in the test code |  | 6 |  | 44313 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test logic | Logic flaws in the test code |  | 7 |  | 44314 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test interface | Flaws in the interface of a component of the test code |  | 8 |  | 44315 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9 |  | 44316 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0 | 44317 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Y/N: | Yes |  |  | Passed | 0 | 44318 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| No |  |  | Passed with issues | 0 | 44319 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Proxy Types: | - |  |  | Failed | Base | 44320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Calculation |  |  | Not tested | New | 44321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Data |  |  | Not applicable | Reusable | 44322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| I/O |  |  |  |  | 44323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Logic |  |  |  |  | 44324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 44325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sizes: | VS | S | M | L | VL | VS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999 | S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
mid | -2 | -1 | 0 | 1 | 2 | M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5 | L | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  | VL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
<-- Mandatory |  | ✔ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Estimated | [10 empty] | Actual
|  |  | Changes to existing code | [5 empty] | New code |  |  |  |  | Changes to existing code | [5 empty] | New code
Component | Type | Relative Size | Base LOC count | Number of LOC modified in base | Number of LOC added to base | Number of LOC deleted from base | Number of base LOC contributing to effort |  | Number of new methods added | LOC/Method | Number of new LOC contributing to effort | Total number of LOC contributing to effort (LOCr) |  | Base LOC count | Number of LOC modified in base | Number of LOC added to base | Number of LOC deleted from base | Number of base LOC contributing to effort |  | Number of new methods added | LOC/Method | Number of new LOC contributing to effort | Total number of LOC contributing to effort (LOCa) | Is this component reusable?
Shift | [6 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
errorReturnStatus | [6 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
validateInputParameters | [6 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
validateIntegrity | [6 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
moveTile | [6 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
moveInDirection | [6 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
checkStatus | [6 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
addRandomTwo | [6 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
createGridList | [6 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
validate2048 | [6 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
findNumber | [6 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
Totals |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
Size Calculation
0
0
0
|  | 0 | Low
Effort Calculation
0
0
0
0
|  | 0 | Low
Estimation: | LOCr= |  | 0
| LOCp= | [12 empty] | Actual: | LOCa= | 0
Ep=
Rationale for override:

## ArcEstimation (hidden)
Size Estimate
Standards
Start date: | 2000-01-01 |  |  | Grades: | AA
End date: | 2020-01-01 |  |  |  | A
Phases: | Planning |  |  |  | AB
| Architecture |  |  |  | B
| Construction |  |  |  | BC
| Refactoring |  |  |  | C
| Integration Test |  |  |  | CD
| Review |  |  |  | D
| Sandbox |  |  |  | F
Postmortem
Defect Types: | Documentation
| Build |  |  | Type | Event
| Product syntax |  |  |  | Response
| Product logic |  |  | Origin | Test Component
| Product interface |  |  |  | Blackbox
| Product checking |  |  |  | User
| Test syntax |  |  |  | External Component (specify)
| Test logic |  |  | Op Spec type | User
| Test interface |  |  |  | Interface
Test checking
Y/N: | Yes
No
Proxy Types: | Calculation
Data
I/O
Logic
Metaphysics: | Object-oriented
Functional
Sizes: | VS
S
M
L
VL
Duration: | LOCe x T
LOCa x T
Productivity
| Estimated |  |  |  |  | Actual
Base Components | Base LOC | Deleted LOC | Modified LOC | Added LOC |  | Base LOC | Deleted LOC | Modified LOC | Added LOC
Totals | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Estimated |  |  |  |  | Actual
New Components | Method Count | LOCr | Reuseable? |  |  | Method Count | LOCa | Reusable?
Totals |  | 0 |  |  |  |  | 0
Actual
Reused Parts | LOC
Totals | 0
Size Calculation
#REF!
0
#REF!
|  | 0 | Low
Effort Calculation
0
#REF!
#REF!
#REF!
|  | 0 | Low
Estimation | LOCr= |  | 0
| LOCp= |  | 0 |  |  | LOCa= | 0
| Ep= |  | 0
Rationale for override:
Note on G66: Indicate only new methods and LOC that resulted from effort. Do not count items that were previously base code and were refactored into new components.

## Plan
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1
End date: | 73051 |  |  | A | 0.95
Phases: | Analyze | Identifying customer needs |  | AB | 0.9
| Architect | High-level design |  | B | 0.85
| Plan project | Determine actions/effort for project duration |  | BC | 0.8
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75
| Construct | Low-level design, coding, unit testing |  | CD | 0.7
| Refactor | Restructure internal design |  | D | 0.65
| Review | Examine test code for risk mitigation |  | F | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful
| Test syntax | Syntax flaws in the test code |  | 6
| Test logic | Logic flaws in the test code |  | 7
| Test interface | Flaws in the interface of a component of the test code |  | 8
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0
Y/N: | Yes |  |  | Passed | 0
| No |  |  | Passed with issues | 0
Proxy Types: | - |  |  | Failed | Base
| Calculation |  |  | Not tested | New
| Data |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS | S | M | L | VL
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999
mid | -2 | -1 | 0 | 1 | 2
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5
| 0 | 0 | 0 | 0
<-- Mandatory |  | ✔
Project Plan Summary
Use this worksheet to record how much production code you plan to write and the amount of time to write it. Record the actual size once the project is complete. The actual time will be calculated from the Time Log. Please note that you are not being evaluated on how close your planned values to your actual values.
Program Size (LOC) |  | Plan | Actual | To Date
Base code LOC count |  | 300 |  | 0
Lines deleted from Base |  |  |  | 0
Lines modified from Base |  |  |  | 0
Lines added to Base |  |  |  | 0
Reused lines |  |  |  | 0
New lines of production code |  | 250 |  | 0
Component Count |  | Plan | Actual | To Date
Reused components |  |  |  | 0
Modified components |  |  |  | 0
New components |  |  |  | 0
Time In Phase (minutes) |  | Plan | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 60 | 60 | 7.407%
Architect |  |  | 0 | 0 | 0%
Plan project |  |  | 0 | 0 | 0%
Plan iteration |  |  | 0 | 0 | 0%
Construct |  |  | 750 | 750 | 92.59%
Refactor |  |  | 0 | 0 | 0%
Review |  |  | 0 | 0 | 0%
Integration test |  |  | 0 | 0 | 0%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 0 | 0 | 0%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  |  | 810 | 810 | 100%
Changes Identified |  |  | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 0 | 0 | 0%
Architect |  |  | 0 | 0 | 0%
Plan project |  |  | 0 | 0 | 0%
Plan iteration |  |  | 0 | 0 | 0%
Construct |  |  | 3 | 3 | 100%
Refactor |  |  | 0 | 0 | 0%
Review |  |  | 0 | 0 | 0%
Integration test |  |  | 0 | 0 | 0%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 0 | 0 | 0%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  |  | 3 | 3 | 100%
Changes Implemented |  |  | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 0 | 0 | 0%
Architect |  |  | 0 | 0 | 0%
Plan project |  |  | 0 | 0 | 0%
Plan iteration |  |  | 0 | 0 | 0%
Construct |  |  | 1 | 1 | 33.33%
Refactor |  |  | 1 | 1 | 33.33%
Review |  |  | 1 | 1 | 33.33%
Integration test |  |  | 0 | 0 | 0%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 0 | 0 | 0%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  |  | 3 | 3 | 100%
Note on C48: Number of lines used from previously-written code
Note on C49: Estimate of the number of lines deleted from previously-written code
Note on C50: Estimated of the number of lines modified from previously-written code
Note on C51: Estimate of the number of lines added to previously-written code to bring it to the point where new functionality can be added
Note on C52: Count of the number of lines of reused source code
Note on C53: Estimate the number of new lines of production code that provide new functionality to meet the specifications of this assignment.
Note on C56: Number of reusable components that will be reused.
Note on C57: Estimate of the number of previously-delivered components that will be used.
Note on C58: Estimate of the number of new components to be built.
Note on C72: Estimate in minutes how much time you plan to expend on this assignment.

## Iterations (hidden)
Iterations
Standards
Start date: | 2000-01-01
End date: | 2025-01-01
Phases: | Planning
Design
Design Review
Code
Code Review
Compile
Test
Postmortem
Documentation
Syntax
Defect Types: | Build, Package
Assignment
Interface
Checking
Data
Function
System
Environment
Y/N: | Yes
No
Proxy Types: | Calculation
Data
I/O
Logic
|  |  | estimation methods | A
Sizes: | VS |  |  | B
| S |  |  | C
| M |  |  | D
L
VL
Duration: | LOCe x T
LOCa x T
Productivity
Component-Iteration Map
| Component | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 5 | Iteration 6 | Iteration 7 | Iteration 8 | Iteration 9 | Iteration 10
Base Components | [11 empty] | 0
0
0
0
0
0
0
0
0
0
New Components | [11 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Number of tasks: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Effort: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS
| Iteration Number | Planned Effort (minutes) | Cumulative Planned Effort | Planned Velocity | Cumulative Planned Velocity | Planned Completion Date
| 1 |  | 0 |  | 0
| 2 |  | 0 |  | 0
| 3 |  | 0 |  | 0
| 4 |  | 0 |  | 0
| 5 |  | 0 |  | 0
| 6 |  | 0 |  | 0
| 7 |  | 0 |  | 0
| 8 |  | 0 |  | 0
| 9 |  | 0 |  | 0
| 10 |  | 0 |  | 0
Calendar
| Day # | Date | Available Minutes | Cumulative Minutes | Planned Velocity | Cumulative Planned Velocity
| 1 | due date - 24 |  | 0 |  | 0
| 2 | due date - 23 |  | 0 |  | 0
| 3 | due date - 22 |  | 0 |  | 0
| 4 | due date - 21 |  | 0 |  | 0
| 5 | due date - 20 |  | 0 |  | 0
| 6 | due date - 19 |  | 0 |  | 0
| 7 | due date - 18 |  | 0 |  | 0
| 8 | due date - 17 |  | 0 |  | 0
| 9 | due date - 16 |  | 0 |  | 0
| 10 | due date - 15 |  | 0 |  | 0
| 11 | due date - 14 |  | 0 |  | 0
| 12 | due date - 13 |  | 0 |  | 0
| 13 | due date - 12 |  | 0 |  | 0
| 14 | due date - 11 |  | 0 |  | 0
| 15 | due date - 10 |  | 0 |  | 0
| 16 | due date - 9 |  | 0 |  | 0
| 17 | due date - 8 |  | 0 |  | 0
| 18 | due date - 7 |  | 0 |  | 0
| 19 | due date - 6 |  | 0 |  | 0
| 20 | due date - 5 |  | 0 |  | 0
| 21 | due date - 4 |  | 0 |  | 0
| 22 | due date - 3 |  | 0 |  | 0
| 23 | due date - 2 |  | 0 |  | 0
| 24 | due date - 1 |  | 0 |  | 0
| 25 | due date |  | 0 |  | 0
| 26 | due date + 1 |  | 0 |  | 0
| 27 | due date + 2 |  | 0 |  | 0
| 28 | due date + 3 |  | 0 |  | 0
| 29 | due date + 4 |  | 0 |  | 0
| 30 | due date + 5 |  | 0 |  | 0
| 31 | due date + 6 |  | 0 |  | 0
| 32 | due date + 7 |  | 0 |  | 0
| 33 | due date + 8 |  | 0 |  | 0
| 34 | due date + 9 |  | 0 |  | 0
| 35 | due date + 10 |  | 0 |  | 0
| 36 | due date + 11 |  | 0 |  | 0
| 37 | due date + 12 |  | 0 |  | 0
| 38 | due date + 13 |  | 0 |  | 0
| 39 | due date + 14 |  | 0 |  | 0
| 40 | due date + 15 |  | 0 |  | 0
| 41 | due date + 16 |  | 0 |  | 0
| 42 | due date + 17 |  | 0 |  | 0

## Summary (hidden)
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1
End date: | 73051 |  |  | A | 0.95
Phases: | Analyze | Identifying customer needs |  | AB | 0.9
| Architect | High-level design |  | B | 0.85
| Plan project | Determine actions/effort for project duration |  | BC | 0.8
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75
| Construct | Low-level design, coding, unit testing |  | CD | 0.7
| Refactor | Restructure internal design |  | D | 0.65
| Review | Examine test code for risk mitigation |  | F | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful
| Test syntax | Syntax flaws in the test code |  | 6
| Test logic | Logic flaws in the test code |  | 7
| Test interface | Flaws in the interface of a component of the test code |  | 8
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0
Y/N: | Yes |  |  | Passed | 0
| No |  |  | Passed with issues | 0
Proxy Types: | - |  |  | Failed | Base
| Calculation |  |  | Not tested | New
| Data |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS | S | M | L | VL
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999
mid | -2 | -1 | 0 | 1 | 2
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5
| 0 | 0 | 0 | 0
<-- Mandatory |  | ✔
Project Plan Summary
Use this worksheet to show how much production code you plan to write and the amount of time to write it. Values are extracted from the Estimation tab.
Program Size (LOC) |  | Plan | Actual | To Date
LOC |  | 0 | 0 | 0
LOCa |  |  |  | 0
Lines added to Base |  | 0 |  | 0
Reused lines |  |  |  | 0
New lines of production code |  | 0 |  | 0
Component Count |  | Plan | Actual | To Date
Reused components |  |  |  | 0
Modified components |  |  |  | 0
New components |  |  |  | 0
Time In Phase (minutes) |  | Plan | Actual | Actual to Date | Actual to Date %
Analyze |  | 0 | 60 | 60 | 7.407%
Architect |  | 0 | 0 | 0 | 0%
Plan project |  | 0 | 0 | 0 | 0%
Plan iteration |  | 0 | 0 | 0 | 0%
Construct |  | 0 | 750 | 750 | 92.59%
Refactor |  | 0 | 0 | 0 | 0%
Review |  | 0 | 0 | 0 | 0%
Integration test |  | 0 | 0 | 0 | 0%
Repattern |  | 0 | 0 | 0 | 0%
Postmortem |  | 0 | 0 | 0 | 0%
Sandbox |  | 0 | 0 | 0 | 0%
TOTAL |  | 0 | 810 | 810 | 100%
Changes Identified |  |  | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 0 | 0 | 0%
Architect |  |  | 0 | 0 | 0%
Plan project |  |  | 0 | 0 | 0%
Plan iteration |  |  | 0 | 0 | 0%
Construct |  |  | 3 | 3 | 100%
Refactor |  |  | 0 | 0 | 0%
Review |  |  | 0 | 0 | 0%
Integration test |  |  | 0 | 0 | 0%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 0 | 0 | 0%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  |  | 3 | 3 | 100%
Changes Implemented |  |  | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 0 | 0 | 0%
Architect |  |  | 0 | 0 | 0%
Plan project |  |  | 0 | 0 | 0%
Plan iteration |  |  | 0 | 0 | 0%
Construct |  |  | 1 | 1 | 33.33%
Refactor |  |  | 1 | 1 | 33.33%
Review |  |  | 1 | 1 | 33.33%
Integration test |  |  | 0 | 0 | 0%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 0 | 0 | 0%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  |  | 3 | 3 | 100%
Note on C50: Estimate of the number of lines added to previously-written code to bring it to the point where new functionality can be added
Note on C51: Count of the number of lines of reused source code
Note on C52: Estimate the number of new lines of production code that provide new functionality to meet the specifications of this assignment.
Note on C55: Number of reusable components that will be reused.
Note on C56: Estimate of the number of previously-delivered components that will be used.
Note on C57: Estimate of the number of new components to be built.

## PlanSummary (hidden)
Project Plan Summary
Standards
Start date: | 2000-01-01 |  | Grades: | AA
End date: | 40179 |  |  | A
Phases: | Analysis |  |  | AB
| Architecture |  |  | B
| Planning |  |  | BC
| Construction |  |  | C
| Refactoring |  |  | CD
| Review |  |  | D
| Integration Test |  |  | F
Postmortem
Sandbox
Defect Types: | Documentation |  | Iteration | NA
| Build |  |  | 1
| Product syntax |  |  | 2
| Product logic |  |  | 3
| Product interface |  |  | 4
| Product checking |  |  | 5
| Test syntax |  |  | 6
| Test logic |  |  | 7
| Test interface |  |  | 8
| Test checking |  |  | 9
| Bad Smell |  |  | 10
Y/N: | Yes
No
Proxy Types: | Calculation
Data
I/O
Logic
Sizes: | VS
S
M
L
VL
|  | Plan | Actual | To Date
Program Size (LOC)
Base code LOC count |  | 0 | 0 | 0
Lines deleted from Base |  | 0 | 0 | 0
Lines modified from Base |  | 0 | 0 | 0
Lines added to Base |  | 0 | 0 | 0
Reused lines |  | #REF! | 0 | 0
New lines of production code |  | #REF! | 0 | 0
|  | Plan | Actual | To Date | To Date %
Time In Phase (minutes)
Analyze |  | 0 | 60 | 60 | 0%
Architect |  | 0 | 0 | 0 | 0%
Plan project |  | 0 | 0 | 0 | 0%
Plan iteration |  | 0 | 0 | 0 | 0%
Construct |  | 0 | 750 | 750 | 0%
Refactor |  | 0 | 0 | 0 | 0%
Review |  | 0 | 0 | 0 | 0%
Integration test |  | 0 | 0 | 0 | 0%
Repattern |  | 0 | 0 | 0 | 0%
Postmortem |  | 0 | 0 | 0 | 0%
Sandbox |  | 0 | 0 | 0 | 0%
TOTAL |  | 0 | 810 | 810 | 0%
Changes traced to the activities below:
Analyze |  |  | 0 | 0
Architect |  |  | 0 | 0
Plan project |  |  | 0 | 0
Plan iteration |  |  | 0 | 0
Construct |  |  | 1 | 1
Refactor |  |  | 0 | 0
Review |  |  | 0 | 0
Integration test |  |  | 0 | 0
Repattern |  |  | 0 | 0
Postmortem |  |  | 0 | 0
Sandbox |  |  | 0 | 0
TOTAL |  |  | 1 | 1
Changes implemented in the activities below:
Analyze |  |  | 0 | 0
Architect |  |  | 0 | 0
Plan project |  |  | 0 | 0
Plan iteration |  |  | 0 | 0
Construct |  |  | 0 | 0
Refactor |  |  | 0 | 0
Review |  |  | 1 | 1
Integration test |  |  | 0 | 0
Repattern |  |  | 0 | 0
Postmortem |  |  | 0 | 0
Sandbox |  |  | 0 | 0
TOTAL |  |  | 1 | 1

## Change Log
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1 | 0 | 44305 | 0
End date: | 73051 |  |  | A | 0.95 | 0 | 0 | 0
Phases: | Analyze | Identifying customer needs |  | AB | 0.9 | 0 | 0 | 0
| Architect | High-level design |  | B | 0.85 | 0 | 0 | 0
| Plan project | Determine actions/effort for project duration |  | BC | 0.8 | 0 | 0 | 0
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75 | 0 | 0 | 0
| Construct | Low-level design, coding, unit testing |  | CD | 0.7 | 44296 | 1 | 0
| Refactor | Restructure internal design |  | D | 0.65 | 44297 | 2 | 5
| Review | Examine test code for risk mitigation |  | F | 0.5 | 44298 | 3 | 10
| Integration test | End-to-end test of components to date |  |  |  | 44299 | 4 | 15
| Repattern | Restructure external design |  |  |  | 44300 | 5 | 20
| Postmortem | Capture post-development statistics |  |  |  | 44301 | 6 | 25
| Sandbox | Prove ideas, try concepts |  |  |  | 44302 | 7 | 30
| Previous Project |  |  |  |  | 44303 | 8 | 35
[6 empty] | 44304 | 9 | 40
[6 empty] | 44305 | 10 | 45
[6 empty] | 44306 | 11 | 50
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow | 44307 | 12 | 55
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful | 44308 | 13 | 0
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful | 44309 | 14 | 0
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral | 44310 | 15 | 0
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful | 44311 | 16 | 0
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful | 44312 | 17 | 0
| Test syntax | Syntax flaws in the test code |  | 6 |  | 44313 | 18 | 0
| Test logic | Logic flaws in the test code |  | 7 |  | 44314 | 19 | 0
| Test interface | Flaws in the interface of a component of the test code |  | 8 |  | 44315 | 20 | 0
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9 |  | 44316 | 21 | 0
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0 | 44317 | 22 | 0
Y/N: | Yes |  |  | Passed | 0 | 44318 | 23 | 0
| No |  |  | Passed with issues | 0 | 44319 | 0 | 0
Proxy Types: | - |  |  | Failed | Base | 44320 | 0 | 0
| Calculation |  |  | Not tested | New | 44321 | 0 | 0
| Data |  |  | Not applicable | Reusable | 44322 | 0 | 0
| I/O |  |  |  |  | 44323 | 0 | 0
| Logic |  |  |  |  | 44324 | 0 | 0
[6 empty] | 44325 | 0 | 0
Sizes: | VS | S | M | L | VL | VS | 0 | 0
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999 | S | 0 | 0
mid | -2 | -1 | 0 | 1 | 2 | M | 0 | 0
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5 | L | 0 | 0
| 0 | 0 | 0 | 0 |  | VL | 0 | 0
[6 empty] | 0 | 0 | 0
<-- Mandatory |  | ✔ |  |  |  | 0 | 0 | 0
Change Log
Use this worksheet to record changes to made to artifacts after the project is underway. Record repairs to defects, as well as changes that result from requirements clarifications/changes.
|  | Change Designation | Description
|  | Requirements Change | Changes to requirements
|  | Requirements Clarification | Clarifications to requirements
|  | Product syntax | Syntax flaws in the deliverable product
|  | Product logic | Logic flaws in the deliverable product
|  | Product interface | Flaws in the interface of a component of the deliverable product
|  | Product checking | Flaws with boundary/type checking within a component of the deliverable product
|  | Test syntax | Syntax flaws in the test code
|  | Test logic | Logic flaws in the test code
|  | Test interface | Flaws in the interface of a component of the test code
|  | Test checking | Flaws with boundary/type checking within a component of the test code
|  | Bad Smell | Refactoring changes (please note the bad smell in the defect description)
Change Number | Date Of Change | Change Type | Activity Where Injected | Iteration Where Injected | Activity Where Removed | Iteration Where Removed | Fix Time | Reference To A Previous Change | Description
1 | 2021-03-24 | Requirements Change | Construct | 1 | Review | 2 | 30 |  | Turns out Integrity is the concatenation of grid and score, not just grid. So my sha256 algorithm was not encrypting correctly.
2 | 2021-03-28 | Test logic | Construct | 2 | Construct | 2 | 30 |  | Decided to change logic of how we were adding the strings of each number to each tile/square. I first decided to iterate -> through each character of the grid string, then decide whether or not it was a "valid number", looking to see if it has a 2nd or 3rd appended integer, then adding it to a list. After walking around a grocery store, it occured to me a more simpler/efficient way of adding these valid numbers to the grid list. I will now iterate through the grid string in increments of 4 and check if that string is a 4 digit valid number, if not then check 3 and so forth...
3 | 2021-03-31 | Test logic | Construct | 2 | Refactor | 2 | 30 |  | I had at first combined vertical/horizontal directions, but combined them since 90% of it were the same code
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75

## Time Log
Constants | [6 empty] | 0
Start date: | 36526 |  | AA |  | Grades: | AA | 1
End date: | 73051 |  | A |  |  | A | 0.95
Phases: | Analyze | 0 | Identifying customer needs |  | AB | 0.9 | 0 | 0
| Architect | 0 | High-level design |  | B | 0.85 | 0 | 0
| Plan project | 0 | Determine actions/effort for project duration |  | BC | 0.8 | 0 | 0
| Plan iteration | 0 | Determine actions/effort this iteration |  | C | 0.75 | 0 | 0
| Construct | 0 | Low-level design, coding, unit testing |  | CD | 0.7 | 44296 | 0
| Refactor | 0 | Restructure internal design |  | D | 0.65 | 44297 | 1
| Review | 0 | Examine test code for risk mitigation |  | F | 0.5 | 44298 | 2
| Integration test | 0 | End-to-end test of components to date |  |  |  | 44299 | 3
| Repattern | 0 | Restructure external design |  |  |  | 44300 | 4
| Postmortem | 0 | Capture post-development statistics |  |  |  | 44301 | 5
| Sandbox | 0 | Prove ideas, try concepts |  |  |  | 44302 | 6
Defect Types: | Requirements Change |  | NA |  | Iteration | NA | did not follow
| Requirements Clarification |  | 1 |  |  | 1 | very painful
| Product syntax |  | 2 |  |  | 2 | painful
| Product logic |  | 3 |  |  | 3 | neutral
| Product interface |  | 4 |  |  | 4 | helpful
| Product checking |  | 5 |  |  | 5 | very helpful
| Test syntax |  | 6 |  |  | 6
| Test logic |  | 7 |  |  | 7
| Test interface |  | 8 |  |  | 8
| Test checking |  | 9 |  |  | 9
| Bad Smell |  | 10 |  |  | 10 | 0
Y/N: | Yes |  | Passed |  |  | Passed | 0
| No |  | Passed with issues |  |  | Passed with issues | 0
Proxy Types: | - |  | Failed |  |  | Failed | Base
| Calculation |  | Not tested |  |  | Not tested | New
| Data |  | Not applicable |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS |  | L |  | M | L | VL
upper | -1.5 |  | 1.5 |  | 0.5 | 1.5 | 99999
mid | -2 |  | 1 |  | 0 | 1 | 2
lower | 0 |  | 0.5 |  | -0.5 | 0.5 | 1.5
| 0 |  | 0 |  | 0 | 0
<-- Mandatory
Time Recording Log
Use this worksheet to record the amount of time you spend on each activity. Use the "sandbox" activity to record time spent experimenting with the assignment requirements..
|  | Activity |  | Meaning
|  | Analyze |  | Identifying customer needs
|  | Architect |  | High-level design
|  | Plan project |  | Determine actions/effort for project duration
|  | Plan iteration |  | Determine actions/effort this iteration
|  | Construct |  | Low-level design, coding, unit testing
|  | Refactor |  | Restructure internal design
|  | Review |  | Examine test code for risk mitigation
|  | Integration test |  | End-to-end test of components to date
|  | Repattern |  | Restructure external design
|  | Postmortem |  | Capture post-development statistics
|  | Sandbox |  | Prove ideas, try concepts
| Start Time |  | Stop Time
Date | Hour | Min | Hour | Min | Interrupt | Delta | Activity | Iteration | Comments
2021-03-23 | 13 | 0 | 14 | 0 |  | 60 | Analyze | 2 | Read the Customer Needs and Description of the project
2021-03-23 | 14 | 0 | 14 |  |  |  |  | 2 | Set up Eclipse, imported the project by setting up the "Team" on project, also created assignment5 branch.
2021-03-24 | 19 | 30 | 20 | 0 |  | 30 |  | 2 | I checked Canvas and saw Umphress's feedback on Assignment4 and his test cases, one failed. I found out that "Integrity" is actually a concatenation of "Score" variable. So my Sha256 was not encrypting correctly, fixing that now.
2021-03-28 | 19 | 0 | 23 | 0 | 60 | 180 | Construct | 2 | Worked on splitting up the given grid string into a list where each index of the list is the spot on the final grid.
2021-03-29 | 11 | 0 | 14 | 0 |  | 180 |  | 2 | Worked on splitting up the given grid string into a list where each index of the list is the spot on the final grid.
2021-03-30 | 19 | 0 | 23 | 0 | 60 | 180 | Construct | 2 | Worked on adding each row in each direction, left, right, up, and down. Was pretty easy once I got one direction figured out. There was a certain pattern, and once I figured it out I could add all the directions up. Also worked on adding random 2 into grid after adding, implemented score functionality, implemented integrity functionality. Excel would not let me say I worked until 1 am. Btw thats what the stop time was.
2021-03-31 | 0 | 0 | 1 | 0 |  | 60 |  | 2
2021-03-31 | 9 | 0 | 10 | 0 |  | 60 | Construct | 2 | Worked on handling exceptions and cases of grid strings that I did not think of. Pretty much trying to break my code
2021-04-01 | 20 | 0 | 23 | 0 | 30 | 150 | Construct | 2 | Worked on exception handling. Interrupt time was from pacing the room thinking.
2021-04-02 | 20 | 0 | 23 | 0 |  | 180 | Construct | 2 | Working on exception handling, deploying to IBM cloud, and writing out this xml.

## Lessons
Lessons Learned
Problems of Importance
1
2
3
4
5
Proposal for Improvements
1
2
3
4
5
Notes and Comments
1 | I think I need to first try to get _shift to identify which numbers are in which tiles. So if I was given "2222444488881616164", I would need to know which location each number is. How do I differentiate 2 and 256? I am thinking tthat I should compare the second number with the first number in the string.
2 | I have an idea of how to execute this. I am going to put all possible numbers of 2048, so [2,4,8,16,32,64,128,256,512,1024,2048] and compare the strings to see if they are in this list. I am trying to think of a more efficient way instead of iterating through and having a bunch of "if" statements, like if the first number is 2 and the second number is 4, then the first tile is 2. But maybe that way is the same efficiency as comparing it to a list?
3
4
5

## Coding Standard
Coding Standard
A coding standard provides a map so that the code generated by a group of programmers will be consistent and, therefore, easier to read and maintain.
This standard applies both to production code and test code.
File headings
Place a doc string at the beginning of each file. The doc string should state the purpose of the file's contents, the date the file was baselined, the date of any modifications subsequent to being baselined, and the name of the author. Each line of the doc string should be indented by four spaces. It can be delimited by either three double quotes or three single quotes. [Rationale: This provides identifying information for the file.]
Example
'''
Created on Sep 20, 2088
@author: David Umphress
'''
Use of docstrings elsewhere is optional. If used, they may be free form; i.e., this coding standard specifies no format.
Comments
Use # for comments other than doc strings. [Rationale: This style of commenting makes comments consistent across other programming languages.]
Example
# Return the answer to the universe
return 42
Do not include comments such as "#end if" to denote end of structural constructs. [Rationale: Indentation gives a visual cue to nesting; comments that indicate end of blocks of code decrease readability.]
Multiple assignment statements
Avoid multiple assignment statements. Use only in situations where readability would be significantly affected by using single assignment statements. [Rationale: Multiple logical lines per physical line result in an inaccurate LOC count.]
|  | Not OK | OK
|  | myVar1, myVar2 = 0, 1 | myVar1 = 0
myVar2 = 1
|  | import os, sys | import os
import sys
Spanning physical lines
Logical lines can span multiple physical lines (where a physical line is no more than 80 characters). In such cases, the continuation lines must be indented one indentation beyond the initial line. Break lines after operators or commas. [Rationale: Indentation improves readability.]
Do not span strings over more than one physical line. In cases where a string won’t fit on a physical line, break the string into individual parts that will fit on a line and concatenate the parts. [Rationale: This simplifies construction of tools that count lines of code.]
|  | Not OK | OK
|  | myVar1 = myVar2 + myVar3 + \ | myVar1 = myVar2 + myVar3 + \
|  | myVar4 | myVar4
|  | myString = '''multi-line | myString='multi-line ’ + \
|  | string''' | ‘string’
Blank lines
Use blank lines to break up related chunks of code. Use at least one blank line between all methods. [Rationale: Blank lines visually segment blocks of related code, thus making it more understandable.]
Code readability
Code should be as self-documenting as possible. For example:
· Identifiers should be given meaningful names that indicate purpose or use.
· Single letters should only be used as names for loop indices when mirroring a mathematical equation specified in the requirements, otherwise, loop indices should be given names that indicate their use.
· Magic numbers – meaning, numbers that appear without explanation in source code – are to be avoided. If they appear, they should be assigned to identifiers that describe their purpose.
· Comments should be used sparingly as an aid to understanding non-intuitive code structure, complex calculations, unique circumstances, etc. It should not be a substitute for unreadable code.
[Rationale: These practices improve comprehension of code.]
Identifier naming
Variables should follow a camel-case convention (i.e., the identifier consists of a series of words with the spaces removed; the beginning letter should be lower case; the beginning letter of each word should be uppercase.)
Class names should be nouns in camel-case, with the first letter capitalized.
Example
class MyClass
Function names and method names should be in camel-case, with the first letter in lower case. The name should connote action and thus should be a verb or verb phrase.
Example
def run()
def getValue()
Methods that retrieve a Boolean object state must use the prefix is in the method name.
Example
isEnabled()
Identifiers designated to be constant should be nouns in all upper case with words separated by an underscore. All other identifiers should be nouns in camel-case, with the first letter in lower case.
Multiple inheritance
Do not use multiple inheritance. [Rationale: This practice decreases understandability.]
File contents
Unless specified otherwise, each class should be stored in its own file. The name of the file should be the name of the class followed by a “.py” extension. For example, class “MyComponent” should be located in a file named “MyComponent.py”.
Test code should be placed in a file whose file name clearly reflects what component is being tested. In all cases, the file name will end with “Test.py”. For example, “MyComponentTest.py” would contain the code that tests “MyComponent.py”.
Smell-specific properties
The following are considered "odious" bad smels:
Dupulicate code: identical or similar code in more than one location.
Side effects: code that, when executed, produces unspecified actions, such as exceptions, output, state changes.
Large class: presence of outward-facing methods that don't support class cohesion.
Large method: lines of code that perform more functionality than can be easily comprehended. Threshold: 25 LOC.
Useless comments: comments that mimic code or detract from code comprehension.
Temporary variables: Use of local variables for multiple purposes across a code segment.
Inappropriate intimacy: taking advantage of implementation details
File structure
Code should be developed in your IDE using the following general directory/file structure:
PyDev Project ... you choose the name.
PyDev Package … as pulled from GitHub
Experimental code folder
Test code folder ... acceptance tests and unit tests
Production code is located in the folder specific to the functionality provided by the assignment, “Rcube” in this case.
Cloud deployment files
Initially pulled from GitHub

## Counting Standard
Counting Standard
A counting standard defines how to determine the number of lines of code.
Each non-blank, non-comment, non-doc string line of production code counts as one line of code. Do not count test code.
Example:
| ''' | doc string … not a line of code
| Created to demonstrate the counting standard | doc string … not a line of code
| Baselined: 1 Aug 2099 | doc string … not a line of code
| Modified: 30 Sep 2099 | doc string … not a line of code
| @author: D. Umphress | doc string … not a line of code
| ''' | doc string … not a line of code
| import math | line of code
| import platform | line of code
blank line … not a line of code
| # Outward facing method(s) | comment … not a line of code
| def prob(parmDictionary): | line of code
| ERROR_HEADER = "error: " | line of code
| ERROR_KEY = "error" | line of code
| SOLUTION_KEY = "probability" | line of code
| DEFAULT_TAILS = 2 | line of code
| resultDict = {} | line of code
blank line … not a line of code
| # Calculate probability | comment … not a line of code
| constant = _calculateConstant(n) | line of code
| integration = _integrate(t, n, _f) | line of code
| if (tails == 1): | line of code
| result = constant * integration + 0.5 | line of code
| else: | line of code
| result = constant * integration * 2 | line of code
blank line … not a line of code
| resultDict[SOLUTION_KEY] = result | line of code
| return resultDict | line of code
blank line … not a line of code
| #--------------------------------------------------------------------------- | comment … not a line of code
| # Internal methods | comment … not a line of code
| def _gamma(x): | line of code
| if (x == 1): | line of code
| return 1 | line of code
| if (x == 0.5): | line of code
| return math.sqrt(math.pi) | line of code
| return (x - 1) * _gamma(x - 1) | line of code
blank line … not a line of code
| def _calculateConstant(n): | line of code
| n = float(n) | line of code
| numerator = _gamma((n + 1.0) / 2.0) | line of code
| denominator = _gamma(n / 2.0) * math.sqrt(n * math.pi) | line of code
| result = numerator / denominator | line of code
| return result | line of code
|  | total LOC: | 28
|  | total number of components: | 3
component 1
|  | name: | prob
|  | method count: | 1
|  | LOC: | 14
component 2
|  | name: | _gamma
|  | method count: | 1
|  | LOC: | 6
component 3
|  | name: | _calculateConstant
|  | method count: | 1
|  | LOC: | 6

## Source (hidden)
Source Code
Paste production source code here. (1) copy your code to the clipboard, (2) click on the "PASTE ME" cell (not the entire row), (3) paste. Do not paste test code.
PASTE ME

## Constants (hidden)
Constants | [5 empty] | 0
Start date: | 2000-01-01 |  |  | Grades: | AA | 100% |  |  | 2021-04-19
End date: | 2100-01-01 |  |  |  | A | 95%
Phases: | Analyze |  | Identifying customer needs |  | AB | 90%
| Architect |  | High-level design |  | B | 85%
| Plan project |  | Determine actions/effort for project duration |  | BC | 80%
| Plan iteration |  | Determine actions/effort this iteration |  | C | 75%
| Construct |  | Low-level design, coding, unit testing |  | CD | 70% | 2021-04-10 | 0 | 0 | AM
| Refactor |  | Restructure internal design |  | D | 65% | 2021-04-11 | 1 | 5 | PM
| Review |  | Examine test code for risk mitigation |  | F | 50% | 2021-04-12 | 2 | 10
| Integration test |  | End-to-end test of components to date |  |  |  | 2021-04-13 | 3 | 15
| Repattern |  | Restructure external design |  |  |  | 2021-04-14 | 4 | 20
| Postmortem |  | Capture post-development statistics |  |  |  | 2021-04-15 | 5 | 25
| Sandbox |  | Prove ideas, try concepts |  |  |  | 2021-04-16 | 6 | 30
[7 empty] | 2021-04-17 | 7 | 35
[7 empty] | 2021-04-18 | 8 | 40
[7 empty] | 2021-04-19 | 9 | 45
[7 empty] | 2021-04-20 | 10 | 50
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow |  | 2021-04-21 | 11 | 55
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful |  | 2021-04-22 | 12
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful |  | 2021-04-23 | 13
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral |  | 2021-04-24 | 14
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful |  | 2021-04-25 | 15
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful |  | 2021-04-26 | 16
| Test syntax | Syntax flaws in the test code |  | 6 |  |  | 2021-04-27 | 17
| Test logic | Logic flaws in the test code |  | 7 |  |  | 2021-04-28 | 18
| Test interface | Flaws in the interface of a component of the test code |  | 8 |  |  | 2021-04-29 | 19
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9 |  |  | 2021-04-30 | 20
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 |  |  | 2021-05-01 | 21
Y/N: | Yes |  |  | Passed |  |  | 2021-05-02 | 22
| No |  |  | Passed with issues |  |  | 2021-05-03 | 23
Proxy Types: | - |  |  | Failed | Base |  | 2021-05-04
| Calculation |  |  | Not tested | New |  | 2021-05-05
| Data |  |  | Not applicable | Reusable |  | 2021-05-06
| I/O | [5 empty] | 2021-05-07
| Logic | [5 empty] | 2021-05-08
2021-05-09
Sizes: | VS | S | M | L | VL | VS
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999 | S
mid | -2 | -1 | 0 | 1 | 2 | M
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5 | L
VL
<-- Mandatory |  | ✔